## Slide 1: Inside Sherpa – Digital Internship
Technology, Strategy & Transformation – Technology Optimisation & Delivery Module

## Slide 2: Project Plan for SectorMetric
•Providing a framework for exception led requirement gathering and use case development.
•Initial market long list of proposed technology solutions.
•Market scan approach and scoring methodology.
•Technology evaluation matrix template and guidance.
.
Our initial understanding of risks, issues and dependencies are as follows:
•You acknowledge that our ability to deliver this piece of work is dependent on you meeting your responsibilities. If responsibilities are not conducted in a timely manner, these will affect project budget, timelines and scope.
•Resource constraints (both internal and client) is a risk that may impact delivery timelines.
•Lack of availability of Subject Matter Experts and relevant stakeholders may present a risk to delivery timelines.
•Availability and agreement of vendors to respond within the timeframes assumed (within a week’s notice) for demos, pricing and contracts discussions.
This project plan will outline how Deloitte will deliver this technology evaluation and selection engagement.
Our understanding
Risks, issues and dependencies

## Slide 3: Project Plan for SectorMetric
This project plan will outline how Deloitte will deliver this technology evaluation and selection engagement.
Guidance: Resource plan and estimation fees are usually broken down into components. This outlines a price tag to the client.
Initial project timeline
Resource plan and estimation of fees
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Activity 1
Activity 2
Weekly Leads Meeting
Activity 3
Milestone
Project status
meeting
Phase
Guidance: Sample project timeline. Populate using the given information.
Position | Daily rate not incl. GST | Number of days over 6 weeks | Total
Partner | $3500 | 2 | $7,000
Director | $3000 | 6 | $18000
Senior Consultant | $1200 | 30 | $36000
Senior Consultant | $1200 | 30 | $36000
 |  | Total | $97,000
Our proposed engagement timelines will span for the total of 6 weeks. In this timeframe we proposed the following phases:
•Phase 1 Technology Evaluation –Consists of providing a framework for exception led requirement gathering and use case development.
•Phase 2 Technology Analysis and Selection –Consist of developing market scan approach and scoring methodology.

## Slide 4
HIGH RISK CONFIDENTIAL
CONFIDENTIAL
PUBLIC